## Slide 1
Magdalena Friedwagner-Maislinger
Elisa Kerschbaumer
Wolfgang Schrattenecker
How to build a budget
Salzburg| Austria | 24.05.2022

## Slide 2: How to build a budget
Application form (AF) is not a budget planning tool
Do the budget calculation outside the AF – use separate tools
Budget planning should be as detailed as possible – think about resources and expenses needed for each cost category
Costs must be proportionate to activities planned
Expected real costs versus eligible project expenditure
Decide for the most appropriate option on how to combine calculation options on cost category level (real costs, flat rates)

## Slide 3: Dimensions of budget calculation
Who? - Project partner
What? - Cost category
When? - Reporting period

## Slide 4: Eligibility – project phases
Pre project phase (project preparation)
Project implementation
Start Controlling Closure
Post project phase (final reporting)
Lump sum
Real costs (incl. flat rates)
Ineligible costs
Approval by the PC – project start date
Deadline: submission final PR
Project closure date

## Slide 5: Eligibility – calculation options

## Slide 6: Eligibility – cost categories
Cost category | Actual costs | Eligible costs | 
Staff costs | Whom (existing or new staff) to involve in project implementation? When and how long? Estimated amount of employment costs? | Real costs or 20% flat rate | 
Office and administration costs | Internal provisions? | 15% flat rate | 40% flat rate
Travel and accommodation costs | How many project meetings/events etc. will take place? Who will take part? Average costs per day? | 10% flat rate | 
External expertise and services costs | Which project activities need external support? Estimated contract value(s)? | Real costs | 
Equipment costs | Which equipment is needed? Estimated costs? | Real costs - depreciation | 

## Slide 7: Budget Simulation Tool

## Slide 8: Example: How to build a budget
Project alpHA, LP AHA
Please calculate the estimated costs of LP AHA per cost category and insert the respective figure under column “estimated costs”.
Please calculate the different options of the eligible budget of LP AHA according to the programme rules and insert the respective figures under “option 1”, “option 2” and “option 3”.
Which calculation option on cost category level (real costs, flat rates) would you select? Please discuss and shortly justify.
If you still have some time (optional): How would you split the eligible budget among reporting periods (no need to calculate in detail)?

## Slide 9: Example: How to build a budget
Cost category | Estimated costs | Eligible budget – according to programme rules |  | 
 |  | option a) | option b) | option c)
Staff costs (a) | 206.440 | 206.440 | 7.800 | 206.440
Office and administration costs (b) | 41.288 | 30.966 | 1.170 | 82.576
Travel and accommodation costs (c) | 14.400 | 20.644 | 780 | 
External expertise and services costs (d) | 36.000 | 36.000 | 36.000 | 
Equipment costs (e) | 3.000 | 3.000 | 3.000 | 
TOTAL (a+b+c+d+e) | 301.128 | 297.050 | 48.750 | 289.016
Project alpHA, LP AHA

## Slide 10: How to build a budget: tips and hints
Read the programme manual carefully
Make a detailed resource and cost plan
Consider potential indexation (but stay realistic)
Ensure sufficient funds for covering the gap between actual costs and project budget, ineligible expenditure items and the post-project phase
Remember the following:
  For staff costs: project assignments to be issued (per employee and reporting period, to be signed ahead of the assignment period)
  For external expertise and service costs: public PP have to observe procurement rules (simplified rules for private PP); consider costs for controller
  For equipment costs: depreciation rules to be considered